## 12 Mar
Issue No | Check Item | URL | Issue Description | Type | Tested Date | Verified Date | Status | Reference Image | Comments
55 | Login >> Create Stylist | http://rohitd.salonchimp.com/merseats/create | I have registered for 5 stylist plan. First I delete one stylist & reload the page then it is showing create stylist button. User can add more than 5 stylist. | Critical | 2013-12-03 |  | corrected
56 | Login >> Appointment >> Booking | http://rohitd.salonchimp.com/users/appointment | Booking is not working. (If user fill wrong phone number the form is submitting but it does not book so form should not be submit). | Critical | 2013-12-03 |  | corrected
57 | Signup >> Registration mail |  | Replace "elcome" to "welcome" in Registration mail format. Give space between "Saloon" & "Chimp" after thanks. | Minor | 2013-12-03 |  | corrected
58 | Login >> Appointment >> Select service | http://rohitd.salonchimp.com/users/appointment | It is not showing any validation message when total time is more than shop time. | Critical | 2013-12-03 |  | corrected |  | Worked on local host.Doesnt made on live server
59 | Login >> Site logo >> Saloonchamp for saloon field >> Customer >> Appointments | http://www.salonchimp.com/ | User has logged out without click on sign out button. | Critical | 2013-12-03 |  | corrected
60 | Login >> Holiday >> Stylist "1" >> Appiontments >> | http://rohitd.salonchimp.com/users/appointment | 1. It is showing all staffs as holiday. 2. but user can add booking in this condition. 3. Holiday section is for single person or for all staff. | Critical | 2013-12-03 |  | corrected |  | Holiday section is for salon not a particular staff member.
61 | admin >> Manage Price plan >> Search by "5" or "6" stylist | http://www.salonchimp.com/pricing | When we search by "5" stylist it is not giving any result. But when search by "6" stylist then it is giving "5" stylist plan. Same for 10 & 20 stylist. | Critical | 2013-12-03 |  | corrected
62 | admin >> Create user >> Edit | http://salonchimp.com/users/update/id/363 | Price plan is not saving if we registere user from "create user" form. | Critical | 2013-12-03 |  | corrected

## 6 Mar
Issue No | Check Item | URL | Issue Description | Type | Tested Date | Verified Date | Status | Reference Image | Comments
16 | Login >> Setting >> Gallery >> create | http://rohit.salonchimp.com/gallery/create | Coding error is showing when we upload image. | Critical | 2013-06-03 |  | Done | Issue16
17 | Login >> Setting >> Gallery >> Delete | http://rohit.salonchimp.com/gallery/admin | Coding error is showing when we Delete image. | Critical | 2013-06-03 |  | Done | Issue17
18 | Login >> Setting >> Account | http://rohit.salonchimp.com/users/settings | Account section is taking long time to open. | Minor | 2013-06-03 | 2013-12-03 | Done
19 | Login>> Setting >> Account | http://rohit.salonchimp.com/users/settings | Coding error is showing & its background color is showing in white color. | Critical | 2013-06-03 | 2013-12-03 | Done | Issue19
20 | Login >> Appointment | http://rohit.salonchimp.com/users/appointment | Look at screenshot. What is the functionality of this field. Please provide label or default text inside the textbox. | Suggestion | 2013-06-03 | 2013-12-03 | Done
21 | Login >> Appointment >> Book | http://rohit.salonchimp.com/users/appointment | No message or email is receiving after booking. | Critical | 2013-06-03 |  | Done
22 | Login >> Appointment >> Book >> Phone Field | http://rohit.salonchimp.com/users/appointment | Phone field is saving non integer values. | Minor | 2013-06-03 |  | Done | Issue22
23 | Login >> Appointment >> Book | http://rohit.salonchimp.com/users/appointment | Appointment booking is performing for past times. | Critical | 2013-06-03 |  | On Hold | Issue23 | Working on Local. Cropped the Past time.Shows Only Current time and future time.
24 | Home >> Forgot Password | http://rohit.salonchimp.com/users/appointment | Coding error is showing in forgot password. | Critical | 2013-06-03 |  | Done | Issue24 | Merchant phone number is showing in Forgot password page.
25 | Home >> Login As admin | http://rohit.salonchimp.com/users/appointment | Copy the url of admin & open this url in other browser. It open admin details without login credential. | Critical | 2013-06-03 | 2013-12-03 | Done
26 | Admin >> User >> Edit | http://salonchimp.com/users/update/id/351 | There is no function to active or Inactive user. But we have provided active/inactive search on user listing. There should be active/inactive link. | Suggestion | 2013-06-03 |  | Done |  | Future Upgrade
27 | login >> Account >> Image >> Delete | http://rohit.salonchimp.com/users/account | Replace message "Are you sure" to "Are you sure you want to delete this". | Minor | 2013-06-03 | 2013-12-03 | Done | Issue27
28 | Admin >> Edit & Create user | http://salonchimp.com/users/create | Both pages taking large time to load & create new page is showing coding error | Critical | 2013-06-03 |  | Done | Issue28 | Error Corrected and page performance increased to some extent
29 | Admin >> Create Services >> name & Category | http://salonchimp.com/users/create | Color of Name & Category should not change if user does not fill both fields. Only validtion message should display. | Suggestion | 2013-06-03 | 2013-12-03 | Done | Issue29
30 | Admin >> User List >> Advance Search | http://salonchimp.com/users/admin | Advance Search is not working. | Critical | 2013-06-03 | 2013-12-03 | Done
31 | Admin >> | http://salonchimp.com/users/admin | Ending part of Company logo is not showing properly. | Critical | 2013-06-03 | 2013-12-03 | Done | Issue31
32 | Admin >> | http://salonchimp.com/users/admin | Names are not showing on Edit/Update & Delete on image button. | Minor | 2013-06-03 |  | Done | Issue32 | Please apply it other admin pages.
33 | Home >> Search by name | http://www.salonchimp.com/site/searchsalon | Listings showing below shop image. | Minor | 2013-06-03 | 2013-12-03 | Done | Issue33
34 | Home>> Search >> View Map | http://www.salonchimp.com/site/searchsalon# | Map popup position is fixed. When we click on view Map link then first it shifts window to upper side then open Map popup. Position should not be fixed. Background is showing very light. | Minor | 2013-06-03 | 2013-12-03 | Done | Issue34
35 | Home >> Search >> | http://www.salonchimp.com/site/searchsalon# | If there is no search result exists then it should display message. | Minor | 2013-06-03 | 2013-12-03 | Done
36 | Home >> Search (IE9) | http://www.salonchimp.com/site/searchsalon | Design has misaligned as we click on Search button. No function is working after search. | Critical | 2013-06-03 |  | Pending | Issue36
37 | Home >> Salonchimp for Salon | http://www.salonchimp.com/site/index | Design of Next & Previous links are not Perfect in Firefox. | Minor | 2013-06-03 |  | Pending | Issue37 | It is showing as that were showing in past.
38 | Home >> Salonchimp for Salon | http://www.salonchimp.com/site/index | Area below Copyright is showing large in firefox. Blank area should not display in all pages of all browsers. (Specially in login page) | Minor | 2013-06-03 |  | Pending | Issue38 | We will apply it on all pages
39 | Home >> Salonchimp for Salon | http://www.salonchimp.com/site/index | Menu bar design in missaligned in ie9. | Minor | 2013-06-03 |  | Pending | Issue39
40 | Home >> Login >> Remember Me (IE9) | http://www.salonchimp.com/site/index | User should not require login details if user is logging after selecting "Remember Me" Checkbox & open same page after closing the browser. | Minor | 2013-06-03 |  | Pending
41 | Home >> Signup >> | http://salonchimp.com/signup?plan=1 | There is exctra space is showing after "Small or Medium or Large" in Design. | Minor | 2013-06-03 | 2013-12-03 | Done | Issue41
42 | Login >> Appointment | http://azad.salonchimp.com/users/appointment | Appointment page design is not proper in Ie9. | Minor | 2013-06-03 |  | Pending | Issue42
43 | Login >> Setting >> Holiday >> Create Hoilday >> Create & Close Field | http://azad.salonchimp.com/users/appointment | Design of Create & Close button design is not proper in IE9. (All create & Edit page) | Minor | 2013-06-03 |  | Pending | Issue43
44 | Login >> Setting >> Services >> Price | http://azad.salonchimp.com/merservices/admin | Replace "rs" to Rupees new symbol. Also in create new page. | Suggestion | 2013-06-03 |  | Done |  | But we have to changed it once again because rupees new sign is not showing properly in window system. Please apply previous pattern.
45 | Login >> Setting >> Services >> Create New | http://azad.salonchimp.com/merservices/create | All fields size should be same on this form. | Suggestion | 2013-06-03 | 2013-12-03 | Done | Issue45
46 | Login >> Setting >> Timings | http://azad.salonchimp.com/mertimings/admin | Days are not center aligned. | Minor | 2013-06-03 | 2013-12-03 | Done | Issue46
48 | Login >> Setting >> Account (IE9) | http://azad.salonchimp.com/users/account | Image is showing below Account form. Remove button is showing as link. | Minor | 2013-06-03 |  | Pending | Issue48
49 | Admin >> Search by id as "10" | http://salonchimp.com/users/admin | It is not giving any result. | Minor | 2013-06-03 | 2013-12-03 | Done | Issue49
50 | Admin >> create user | http://salonchimp.com/users/admin | Image is showing large when we create user from admin with image. | Critical | 2013-06-03 | 2013-12-03 | Done | Issue50
51 | Admin >> Manage Services >> Advance search | http://salonchimp.com/services/admin | There is no user of id field on this page. Also design in not proprer in this page. | Minor | 2013-06-03 | 2013-12-03 | Done | Issue51A & 51B
52 | Admin >> Manage Services >> Advance search >> Search by "Description" | http://salonchimp.com/services/admin | it is showing coding error. | Critical | 2013-06-03 |  | Done | Issue52
53 | Admin >> Create user >> Submit without filling form | http://salonchimp.com/users/create | Password form showing as filled password. | Minor | 2013-06-03 |  | Done | Issue53
54 | Admin >> 403 & 404 error design (IE9) | http://salonchimp.com/users/create | 403 & 404 errors have design issues in ie9. | Minor | 2013-06-03 |  | Pending | Issue54A & Issue54B

## 5 Mar
Issue No | Check Item | URL | Issue Description | Type | Tested Date | Verified Date | Status | Reference Image | Comments
1 | Home>> Sign up >> Username | http://www.salonchimp.com/signup?plan=1 | There is no limit on username field. It is saving single character. | Minor | 2013-05-03 | 2013-12-03 | Done
2 | Home>> Sign up >> Mobile | http://www.salonchimp.com/signup?plan=1 | Mobile field is saving non numeric values & also it is saving sing digit as phone number. Apply limit on phone field. | Minor | 2013-05-03 |  | Done |  | apllied same changes on Create user page on admin.
3 | Home>> Sign up >> Password & Confirm Password | http://www.salonchimp.com/signup?plan=1 | Password is saving single characters values & also it is saving spaces between password values like as "test 123". | Minor | 2013-05-03 |  | Done |  | apllied same changes on Create user page on admin.
4 | Home>> Sign up >> City | http://www.salonchimp.com/signup?plan=1 | City field is saving single characters values. Apply limit on City field. | Minor | 2013-05-03 | 2013-08-03 | Done
5 | Login>> Select Service >> Sliming | http://rohit.salonchimp.com/users/appointment | There are some design issues. Look at Screenshot. | Minor | 2013-05-03 | 2013-12-03 | Done | Issue5A, 5B, 5C
6 | Login >> Customers >> Create New >> Mobile | http://rohit.salonchimp.com/mercustomers/create | Mobile field is saving non numeric values & also it is saving sing digit as phone number. Apply limit on phone field. | Minor | 2013-05-03 | 2013-12-03 | Done
7 | Login >> Customers >> Create New >> Email | http://rohit.salonchimp.com/mercustomers/create | Validation is not working on Email field. | Critical | 2013-05-03 | 2013-12-03 | Done
8 | Login >> Customers >> Create New >> Close | http://rohit.salonchimp.com/mercustomers/create | It opens manage Stylist page. | Critical | 2013-05-03 | 2013-12-03 | Done
9 | Login >> Setting >> Manage Holiday >> Update | http://rohit.salonchimp.com/merholidays/update/id/7 | Replace "Upadte Holiday" to "Update Holiday" in Breadcumbs. Also it is showing text "Merholidays" in header. | Minor | 2013-05-03 | 2013-12-03 | Done
10 | Login >> Setting >> Manage Holiday >> Delete | http://rohit.salonchimp.com/merholidays/update/id/7 | Replace Message "Are you sure you want to delete this item?". Please remove item from this message. | Minor | 2013-05-03 | 2013-12-03 | Done
11 | Login >> Setting >> Stylelist >> Create New | http://rohit.salonchimp.com/merseats/create | Coding error is showing as we click on Create New link. | Critical | 2013-05-03 | 2013-12-03 | Done | Issue11
12 | Login >> Setting >> Services >> Create New >> Price & Duration | http://rohit.salonchimp.com/merservices/create | both fields are not taking values like as 2.30 or 10.30 | Minor | 2013-05-03 | 2013-12-03 | Done |  | Prices are in multiple of Rs(hence we cant put Rs10 & paise 30), Time is multiple of minutes not hours hence we cant put 2.30 hours instead we input 90 minutes)
13 | Login >> Setting >> Services >> search by Active & Inactive | http://rohit.salonchimp.com/merservices/create | Coding error is showing. | Critical | 2013-05-03 | 2013-12-03 | Done | Issue13
14 | Login >> Setting >> Offers >> Id | http://rohit.salonchimp.com/deals/admin | There is no use of id, I think it should be remove. | Suggestion | 2013-05-03 |  | Hold |  | Will remove after further discussion.
15 | Login >> Setting >> Offer >> Create offer >> Valid | http://rohit.salonchimp.com/deals/create | Calender is showing year from 1970 to 1980. | Critical | 2013-05-03 | 2013-12-03 | Done